## Instructions
BUSINESS UNIT RISK REGISTER INSTRUCTIONS
Overview
We all manage risks as part of our day job. Managing risk is a core management responsibility, as we identify and manage the threats to achieving our objectives; individual, business unit and corporate. In so doing, we identify opportunities to improve our performance. Hence, risk management cannot be solely delegated to Internal Audit, Operational and/or Regulatory business units, but must be embedded totally.
Objective
The objectives of risk management are:
· To ensure decisions take account of risk;
· To focus management attention on risks that need intervention;
· To deliver all regulatory & legal obligations and satisfy all corporate governance requirements; and
· To protect shareholder value and other stakeholder interests.
Purpose of this Document
To support all business units in managing risks in a structured format and enable visibility and assurance/governance to the [name organisation] Board.
Responsibilities
The Division Leads are responsible for ensuring the business unit risk register is maintained and include all risks and opportunities captured during the risk process. All risks should be quantified, evaluated and categorised ensuring each risk has a Senior Management Team (SMT) risk owner, risk response plan, completion date and response plan owner. Progress against risk response plans is reviewed based on significance by the Business Unit Risk Advisor in conjunction with the SMT Risk Owner.
Risk Register Instructions
Please complete the risk register as follows:
a. Mandatory identification fields should be completed: Business Unit, SMT Member and Date
b. For each individual risk; risk category, risk description/cause/consequence, date entered the risk register, financial impact of the risk (estimated), 'impact' score, 'likelihood' score, SMT risk owner, risk response plan, completion date, response plan owner, 'how well is this risk understood and managed' and target risk fields must be completed. In addition, the directional arrows should be used to indicate movement from the last quarterly business unit risk register report submitted.
c. For help determining the individual risk ranking (risk category, 'impact' score, 'likelihood' scores) and quarterly escalation criteria, please refer to the ranking and escalation worksheet tab in this document.
d. Once the risk assessment is complete the focus of attention should shift to the risk response plans. These plans should be written in sufficient detail including current status and the ability to meet the completion date. In addition, a named response plan owner that will be responsible for ensuring the response plans are completed must be clearly identified.
e. Lastly we assess how we are managing the risk and our target risk: 'How well is this risk understood and managed?' assessment is based on colour coding: Red (there is no action plan to mitigate the risk, or current activities are ineffective), Amber (the plan exists, but is not fully rolled out) or Green (Green should equate to the plan that is fully implemented). Target risk assessment after the implementation of the risk response plan is based on colour coding: Red (High risk), Amber (Medium risk) and Green (Low risk). For both questions, directional arrows show a change since the last report. A down arrow shows a move closer to reaching a green rating.
Quarterly Reporting Requirements
On a quarterly basis, Risk Advisors identify material risks that are escalated as part of the Corporate Risk Reporting Process. Escalation of risks is based on risk thresholds (refer to the ranking and escalation criteria tab in this workbook), the respective objectives and KPI’s in that business area. Internal Audit will work with the Risk Advisor to provide independent challenge of the business unit risk register prior or during an SMT member risk review. After the relevant SMT member review, the Risk Advisors escalates these risks for submission to Internal Audit. Internal Audit will review all escalated business risks from across Save the Children with the objective of establishing the top corporate risks for escalation to the SMT and SLT.
Risk Management Assistance
Please feel free to contact the following team members for detailed advice on the implementation of the corporate risk management policy and process:
Name
Add email and phone no:'s
Name
Add email and phone no:'s

## Format Guide
FORMAT GUIDE - BUSINESS UNIT RISK REGISTER
BUSINESS UNIT: |  | FLEET MANAGEMENT (EXAMPLE)
EMT MEMBER: |  | JANE DOE
RISK ADVISOR: |  | JOE COMMONS
DATE: |  | 2021-08-21
Current Risk
ID | Risk Category | Risk Description | Risk Cause | Risk Consequence | Date Entered Risk Register | Financial Impact of Risk (USD in millions) | Impact |  | Likelihood |  | Combined Score | EMT Risk Owner | Risk Response Plan | Completion Date | Response Plan Owner | How well is the risk understood and managed? | Target Risk
Date
Entered
Register
EG1 | Finance | Fleet management system is no longer supported by the vendor. | Historic support agreements were not extensive and business did not choose to extend legacy system support. | Systems unable to include new fleets, performance reports are incomplete, and historic data cannot be recovered if system breaks down | 2021-06-30 | 5 | ↑ | 4 | — | 2 | 8 | Jane Doe | The scope of a new FMS project has been approved and covers Back Office, Cost Allocation Billing and Trip Booking. The expected go live date for all work streams is January 2022. ROST were appointed as preferred supplier on July 1st and the project is expected to mobilise on September 1st subject to final agreement of the contract. | 2019-11-13 | Mickey Mouse | ↑ | —
1 | [6 empty] | — | 0 | — | 0 | 0 |  |  |  |  | — | —
2 | [6 empty] | — | 0 | — | 0 | 0 |  |  |  |  | — | —
3 | [6 empty] | ↑ | 0 | — | 0 | 0 |  |  |  |  | — | —
4 | [6 empty] | — | 0 | ä | 0 | 0 |  |  |  |  | — | —
5 | [6 empty] | — | 0 | — | 0 | 0 |  |  |  |  | — | —
6 | [6 empty] | — | 0 | ä | 0 | 0 |  |  |  |  | ↑ | —
7 | [6 empty] | — | 0 | — | 0 | 0 |  |  |  |  | — | —
8 | [6 empty] | — | 0 | ↓ | 0 | 0 |  |  |  |  | — | —
9 | [6 empty] | — | 0 | — | 0 | 0 |  |  |  |  | — | ↓
10 | [6 empty] | ↓ | 0 | — | 0 | 0 |  |  |  |  | — | —
| Key | Financial Impact | Potential financial impact, estimated
|  | Impact, likelihood | Scale of 1 (low) to 5 (high), - = steady since last time, ã increased, ä decreased
|  | Combined score | Impact multiplied by probability, colour determined automatically according to heat map
|  | How well is risk understood and managed? | RED = | There is no plan to mitigate the risk, or current activities are ineffective.
|  |  | AMBER = | The plan exists, but it is not fully rolled out.
|  |  | GREEN = | The plan is fully implemented.
Directional arrows show a change since the last report. A down arrow shows a move closer to reaching a green rating.
|  | Target risk rating? | RED = | High risk
|  |  | AMBER = | Medium risk
|  |  | GREEN = | Low risk
1
Mandatory identification fields
5
4
3
2
The impact and likelihood score (before controls) are shown in these columns.
Each time risks are reviewed, arrows can be used to show the evolution of the current risk scores since last time they were reviewed by using one of the following:
— Steady since last time
↑ Increased
↓ Decreased
Try to supply a figure for the potential financial impact in the Commentary box, whether it is a financial risk or not. This may need to be a broad estimate.
Red equates to a high risk, Amber highlights a medium risk and Green shows a low risk after the implementation of the risk response plan.
The arrows display the evolution of the response over time. Green should equate to the plan that is fully implemented. Amber for showing the plan exists, but is not fully rolled out. Red shows there is no plan to mitigate the risk.
This is the combined score, calculated by multiplying the impact and likelihood scores. The colour is determined as per the Risk Assessment Criteria.
Green
Amber
Red
Both cells have drop down menus for upwards arrow (increase, moving to red rating), downwards arrow (decrease, moving to green rating) and no change .

## Business Unit Risk Register
F
BUSINESS UNIT: |  | Fleet Management
SMT MEMBER:
RISK ADVISOR:
DATE:
Current Risk
ID | Risk Category | Risk Description | Risk Cause | Risk Consequence | Date Entered Risk Register | Financial Impact of Risk (£m) | Impact | Likelihood | Combined Score | SMT Risk Owner | Risk Response Plan | Completion Date | Response Plan Owner | How well is the risk understood and managed? | Target Risk
Date
Entered
ID |  |  |  |  | Register
0
0
0
0
0
0
0
0
0
0
0
| Key | Financial Impact | Potential financial impact, estimated
|  | Impact, likelihood | Scale of 1 (low) to 5 (high), - = steady since last time, ã increased, ä decreased
|  | Combined score | Impact multiplied by probability, colour determined automatically according to heat map
|  | How well is risk understood and managed? | RED = | There is no plan to mitigate the risk, or current activities are ineffective.
|  |  | AMBER = | The plan exists, but it is not fully rolled out.
|  |  | GREEN = | The plan is fully implemented.
Directional arrows show a change since the last report. A down arrow shows a move closer to reaching a green rating.
|  | Target risk rating? | RED = | High risk
|  |  | AMBER = | Medium risk
|  |  | GREEN = | Low risk
↑
—
↓
Green
Amber
Red

## Risk Assessment & Escalation
BUSINESS RISK ASSESSMENT & ESCALATION CRITERIA
The following tool should be used to quantify business risks by following steps 1-5.
Risk Assessment
• By scoring risks for Impact and Occurrence, we can gauge an individual risk's effect on the business.
• This allows us to compare and rank risks.
• The initial 'score' for each risk should represent the outcome if controls existed in the business.
• Management make assessments of how well the risk is understood and how good the current controls are.
• Each numbered step below corresponds to a different column on the final format.
| 1 | 2 | 3 |  | 4 |  | 5
Risk Category | Insignificant | Minor | Moderate |  | Major |  | Severe
Reputational & Stakeholder Relationship | Reputation impacts can be readily managed and working relationship with stakeholders maintained | Localised impact on reputation and engagement with stakeholders reducing ability to deliver short term or localised objectives | Short term adverse effect on reputation and engagement with stakeholders and ability to promote and achieve strategic business objectives |  | Major adverse and/or long term effect on reputation and engagement with stakeholders and ability to promote and achieve strategic business objectives |  | Sustained opposition from stakeholders that will prevent achievement of short and long-term strategic objectives
Regulatory | No potential for failure of end of year regulatory targets or requirements. Strong likelihood that issue can be resolved before next regulatory report therefore issue not reported to Regulators | Minimal potential for failure of end of year regulatory targets or requirements. Notification from Regulators of concerns with likely requests for more detailed information and/or remedial action plans. Minor impact on reputation with Regulators. Minor threat to achievement of price review objectives | Failure to meet regulatory targets or requirements resulting in formal Notices and/or investigations by the Regulators. Additional regulatory reporting requirements (e.g. quarterly as well as annual reporting) with associated independent certification. Short term adverse effect on reputation and engagement with stakeholders. Moderate threat to achievement of price review objectives |  | Failure or persistent failure to meet regulatory targets or requirements resulting in formal Notices and/or investigations by the Regulators. Major adverse effect on reputation and engagement with stakeholders. Major threat to achievement of price review objectives |  | Potential revocation of regulatory licence
Legal | Interference with private rights (only) for which compensation payments are not expected to exceed [£10k] in aggregate | Interference with private rights for which compensation payments are not expected to exceed [£100k] in aggregate | Interference with private rights for which compensation payments are expected to exceed [£100k] in aggregate and/or risk of criminal proceedings in the court and/or regulatory investigation |  | Interference with private rights for which compensation payments are expected to exceed [£500k] in aggregate and/or risk of criminal proceedings in the Courts |  | Breach of legislation with potential to result in personal criminal liability for directors and/or managers of the company
Environment | Environment incident, regulatory non-compliance or performance failure managed internally (near miss) with no consequences but learning points recorded | Environment incident, regulatory non-compliance or performance failure with no direct consequences but leads to either an internal investigation and/or is externally reported | Environment incident, regulatory non-compliance or performance failure which leads to an external investigation/prosecution or other enforcement action at Courts with a ceiling to any fine |  | Environment incident, regulatory non-compliance or performance failure which leads to an external investigation/prosecution or other enforcement action at Courts with unlimited fine |  | Environment incident, regulatory non-compliance or performance failure with widespread or lasting impact resulting in a public inquiry or investigation or criminal liability for directors
Health & Safety | Minor injury or incident | Multiple minor injuries or incidents | Serious injury or incident |  | Multiple serious injuries or incidents |  | Single fatality
Operations | Minor interruption to non-critical process | Interruption to non-critical process | Lengthy interruption to non-critical process |  | Interruption to critical process |  | Major interruption to critical process
Management Effort | Minor impact on management | Issue requiring senior management intervention | Interruption to management |  | Material interruption to management |  | Critical impact on ability to manage
People | No impact to employee recruitment / satisfaction / retention | Minor negative impact to employee recruitment / satisfaction / retention | Moderate negative impact to employee recruitment / satisfaction / retention |  | Serious negative impact to employee recruitment / satisfaction / retention |  | Severe negative impact to employee recruitment / satisfaction / retention
Customer Relationship | No impact to customer satisfaction / retention | Minor negative impact to customer satisfaction / retention | Moderate negative impact to customer satisfaction / retention |  | Serious negative impact to customer satisfaction / retention |  | Severe negative impact to customer satisfaction / retention
Financial | Between £50k and £200k | Between £200k and £500k | Between £500k and £1m |  | Between £1m and £5m |  | Greater than £5m
Try to estimate the monetary impact of the event occurring. E.g. The value of a fine or expected loss in turnover.
Project-related risks as well as ongoing business risks should be included in the risk register.
Assessment |  | Score
Almost Certain (80-100%) |  | 5
Likely (50-80%) |  | 4
Moderate (25-50%) |  | 3
Unlikely (5-25%) |  | 2
Remote (<5%) |  | 1
By multiplying the impact and occurrence scores, we can gauge the level of current risk posed before future risk response actions are applied. The colours are decided as follows:
Key |  |  | 5 | 10 | 15 | 20 | 25
RED = HIGH RISK |  |  | 4 | 8 | 12 | 16 | 20
AMBER = MEDIUM RISK |  |  | 3 | 6 | 9 | 12 | 15
GREEN = LOW RISK |  |  | 2 | 4 | 6 | 8 | 10
|  |  | 1 | 2 | 3 | 4 | 5
This Combined Score is displayed as a traffic light colour with the score shown in the centre.
Insert SMT Risk Owner, Risk Response Owner, Risk Response Plan Commentary and Completion Date
Identify the SMT risk owner and response plan owner, provide commentary on risk response plans with sufficient detail, including current status and the ability to meet the completion date.
How well is the risk understood and managed?
A traffic light colour is chosen to specify this. This is not related to the colour calculated in step 2.,
RED = | There is no plan to mitigate the risk, or current activities are ineffective.
AMBER = | The plan exists, but it is not fully rolled out.
GREEN = | The plan is fully implemented.
Directional arrows show a change since the last report. A down arrow shows a move closer to reaching a green rating.
What is the target risk we are aiming for after implementing the risk response plan?
A final traffic light is chosen to highlight the target risk we are aiming for.
RED = | High Risk
AMBER = | Medium Risk
GREEN = | Low Risk
Directional arrows show a change since the last report. A down arrow shows a move closer to reaching a green rating.
Risk Escalation Criteria
On a quarterly basis risks are escalated from business units to Internal Audit enabling the Risk Portfolio and the Top Corporate Risks to be determined and presented to the SMT and the Board, I.e. Corporate Risk Reporting Process.
The Business Unit Risk Escalation Threshold set at:
Likelihood of Occurrence Score * Financial Impact of Risk (column G in the Risk Register) greater than £1m or there is a specific reputational risk of significance.
Choose a 'Likelihood of Occurrence' Score based on the appropriate criteria
Choose a Risk Category and a 'Magnitude of Impact' Score. Add risk category, description, cause, consequence, date and financial impact and impact score to risk register
Magnitude of Impact
Likelihood of
Occurrence
1
2
3
5
4

## Definitions
RISK MANAGEMENT DEFINITIONS
ARRC: Audit & Risk Review Committee
Cause: The situation(s) that would have to exist in order for the risk to occur
Completion Date: Date on which risk response plan is to be completed by the risk response owner
Consequence: The effects on the achievement of an objective once the risk has occurred
Corporate Risk Management Policy and Process: The policy and process of managing risks to the achievement of corporate objectives
Corporate Risk Reporting Process: Quarterly risk reporting process that escalates significant risks to the SMT
Current Risk: The assessment of the risk as it stands at this point in time, taking into account current controls
SMT: Senior Management Team
SMT Risk Owner: SMT member that that has overall responsibility for a risk
Financial Impact: Current or future impact of risk expressed in monetary terms (£m)
Heat Maps: Diagrammatic method of graphing risk impact and likelihood
Impact: The potential loss should the consequence occur. It describes the scale of the consequence in terms of severity and duration
Likelihood: How likely the risk is to occur within a given timescale
Probability: The likelihood, expressed as a percentage that the risk would materialise within a given period of time
Reporting Timetable: Timetable for reporting escalated risks to Internal Audit and the SMT
Response Plan Owner: The person assigned to deliver and maintain the agreed response plan
Risk is:
· An event/uncertainty that threatens the achievement of any business objective; and/or
· A circumstance that could compromise the safety and security of our customers and staff;
· That will/may affect the financial sustainability or strength of the business.
Risk Advisor – The person who is to advise on all risk management development and provide risk advice within their relevant business area
Risk Appetite: The overall amount of risk the organisation is prepared to tolerate/be exposed to at any point in time determined by the Board and the SLT
Risk Assessment: The qualitative or quantitative assessment of a risk
Risk Category: Categories which risks are grouped in to aid in identification. Examples are: Financial, Reputational, Health & Safety, Environmental, Regulatory, Legal, Programme Disruption, Management Effort.
Risk Description: A description that conveys the uncertainty of the risk circumstances, any underlying assumptions and consequences
Risk Identification: The process of identifying risk with a bi-product of recording those risks in a risk register
Risk Owner: The person or organisation who is accountable for managing the risk and ensuring that the agreed risk response plan actions are delivered
Risk Portfolio: Document prepared at a corporate level which ranks all risks escalated form the business units
Risk Register: The record of identified risks, which maintains such information as, risk description, financial impact, likelihood, risk response plans and owners
Risk Response Plan: The agreed management action(s) that are designed to lessen one or more of the following:
The likelihood of the risk occurring; and
The consequence if the risk were to occur
Stakeholder: Any party who may have an interest in or obligation to the risk management process and/or the management of individual risks
Target Risk: Level of risk that is targeted after the risk response plan is fully implemented